## Foundation Setup
Task Name | Description | Target Env | Execution
Repository & Image Assessment | Analyze ECR, repositories, unique images, DataPower, MuleSoft | DEV | One-time
JFrog Docker Repository Setup | Create Docker and virtual repositories in Artifactory | DEV | Sequential
Programmatic Docker Authentication & Validation | Enforce and validate Docker login via tokens for push/pull operations | DEV → QA → PROD | Sequential
Security Exception Approval | Obtain approval for excluding DataPower and MuleSoft | DEV | One-time
Docker Push/Pull Validation | Validate push/pull workflows for virtual repositories | DEV | Sequential
ECR to JFrog Migration Setup | Enable automated migration of Docker images from ECR to JFrog | DEV | Sequential

## Security Governance
Task Name | Description | Target Env | Execution
OPA Policy Enforcement | Ensure images are pulled only from JFrog | DEV → QA → PROD | Sequential
Conjur Credential Integration | Configure JFrog credentials securely | DEV → QA → PROD | Sequential
JFrog Xray Integration | Enable vulnerability scanning | DEV → QA → PROD | Parallel
Wiz Security Integration | Scan images before push | DEV → QA → PROD | Parallel
CI/CD Security Enforcement | Fail pipeline on vulnerabilities | DEV → QA → PROD | Sequential
OPA for Wiz | Enforce Wiz scan compliance | DEV → QA → PROD | Sequential

## CI-CD Enablement
Task Name | Description | Target Env | Execution
Harness Image Pull Secret Setup | Create image pull secrets in EKS | DEV → QA → PROD | Sequential
CI Pipeline Implementation | Build pipelines using JFrog images | DEV → QA → PROD | Parallel
CD Pipeline with Rollback | Deploy and rollback pipelines | QA → PROD | Sequential
Branch Promotion Strategy | Promote images via GitHub strategy | QA → PROD | Sequential
Image Pull Secret Automation | Automate secret updates in EKS | DEV → QA → PROD | Parallel

## Image Management
Task Name | Description | Target Env | Execution
Base Image Curation | Maintain curated base images | DEV → QA → PROD | Ongoing
Golden Image Upload | Upload approved images after scan | DEV → QA → PROD | Sequential
Image Promotion Workflow | Promote images across environments | DEV → QA → PROD | Sequential

## Environment Setup
Task Name | Description | Target Env | Execution
Environment Segregation | Separate Non-Prod and Prod | DEV → QA → PROD | One-time
Artifactory URL Standardization | Update production URLs | PROD | One-time
Terraform Automation | Create connectors via Terraform | DEV → QA → PROD | Parallel

## Advanced
Task Name | Description | Target Env | Execution
Lambda Integration | Enable Lambda with JFrog images | QA → PROD | Sequential
Advanced Pipeline Automation | Automate image lifecycle | DEV → QA → PROD | Parallel